## Sheet1
Project Tasks
Id | Level | Name | Progress | Start | Due | User | Completion Date | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk | Baseline: Start Date | Baseline: Due Date | Duration (Cal. Days) | Working Days | 06/05/2019 | 07/05/2019 | 08/05/2019 | 09/05/2019 | 10/05/2019 | 11/05/2019 | 12/05/2019 | 13/05/2019 | 14/05/2019 | 15/05/2019 | 16/05/2019 | 17/05/2019 | 18/05/2019 | 19/05/2019 | 20/05/2019 | 21/05/2019 | 22/05/2019 | 23/05/2019 | 24/05/2019 | 25/05/2019 | 26/05/2019 | 27/05/2019 | 28/05/2019 | 29/05/2019 | 30/05/2019 | 31/05/2019 | 01/06/2019 | 02/06/2019 | 03/06/2019 | 04/06/2019 | 05/06/2019 | 06/06/2019 | 07/06/2019 | 08/06/2019 | 09/06/2019 | 10/06/2019 | 11/06/2019 | 12/06/2019 | 13/06/2019 | 14/06/2019 | 15/06/2019 | 16/06/2019 | 17/06/2019 | 18/06/2019 | 19/06/2019 | 20/06/2019 | 21/06/2019 | 22/06/2019 | 23/06/2019 | 24/06/2019 | 25/06/2019 | 26/06/2019 | 27/06/2019 | 28/06/2019 | 29/06/2019 | 30/06/2019 | 01/07/2019 | 02/07/2019 | 03/07/2019 | 04/07/2019 | 05/07/2019 | 06/07/2019 | 07/07/2019 | 08/07/2019 | 09/07/2019 | 10/07/2019 | 11/07/2019 | 12/07/2019 | 13/07/2019 | 14/07/2019 | 15/07/2019 | 16/07/2019 | 17/07/2019 | 18/07/2019 | 19/07/2019 | 20/07/2019 | 21/07/2019 | 22/07/2019 | 23/07/2019 | 24/07/2019 | 25/07/2019 | 26/07/2019 | 27/07/2019 | 28/07/2019 | 29/07/2019 | 30/07/2019 | 31/07/2019 | 01/08/2019 | 02/08/2019 | 03/08/2019 | 04/08/2019 | 05/08/2019 | 06/08/2019 | 07/08/2019 | 08/08/2019 | 09/08/2019 | 10/08/2019 | 11/08/2019 | 12/08/2019 | 13/08/2019 | 14/08/2019 | 15/08/2019 | 16/08/2019 | 17/08/2019 | 18/08/2019 | 19/08/2019 | 20/08/2019 | 21/08/2019 | 22/08/2019 | 23/08/2019 | 24/08/2019 | 25/08/2019 | 26/08/2019 | 27/08/2019 | 28/08/2019 | 29/08/2019 | 30/08/2019 | 31/08/2019 | 01/09/2019 | 02/09/2019 | 03/09/2019 | 04/09/2019 | 05/09/2019 | 06/09/2019 | 07/09/2019 | 08/09/2019 | 09/09/2019 | 10/09/2019 | 11/09/2019 | 12/09/2019 | 13/09/2019 | 14/09/2019 | 15/09/2019 | 16/09/2019 | 17/09/2019 | 18/09/2019 | 19/09/2019 | 20/09/2019 | 21/09/2019 | 22/09/2019 | 23/09/2019 | 24/09/2019 | 25/09/2019 | 26/09/2019 | 27/09/2019 | 28/09/2019 | 29/09/2019 | 30/09/2019 | 01/10/2019 | 02/10/2019 | 03/10/2019 | 04/10/2019 | 05/10/2019 | 06/10/2019 | 07/10/2019 | 08/10/2019 | 09/10/2019 | 10/10/2019 | 11/10/2019 | 12/10/2019 | 13/10/2019 | 14/10/2019 | 15/10/2019 | 16/10/2019 | 17/10/2019 | 18/10/2019 | 19/10/2019 | 20/10/2019 | 21/10/2019 | 22/10/2019 | 23/10/2019 | 24/10/2019 | 25/10/2019 | 26/10/2019 | 27/10/2019 | 28/10/2019 | 29/10/2019 | 30/10/2019 | 31/10/2019 | 01/11/2019 | 02/11/2019 | 03/11/2019 | 04/11/2019 | 05/11/2019 | 06/11/2019 | 07/11/2019 | 08/11/2019 | 09/11/2019 | 10/11/2019 | 11/11/2019 | 12/11/2019 | 13/11/2019 | 14/11/2019 | 15/11/2019 | 16/11/2019 | 17/11/2019 | 18/11/2019 | 19/11/2019 | 20/11/2019 | 21/11/2019 | 22/11/2019 | 23/11/2019 | 24/11/2019 | 25/11/2019 | 26/11/2019 | 27/11/2019 | 28/11/2019 | 29/11/2019 | 30/11/2019 | 01/12/2019 | 02/12/2019 | 03/12/2019 | 04/12/2019 | 05/12/2019 | 06/12/2019 | 07/12/2019 | 08/12/2019 | 09/12/2019 | 10/12/2019 | 11/12/2019 | 12/12/2019 | 13/12/2019 | 14/12/2019 | 15/12/2019 | 16/12/2019 | 17/12/2019 | 18/12/2019 | 19/12/2019 | 20/12/2019
GZfZVfn6ceK9o7Grt9Nh | 1 | Customer Database: | 0% | [12 empty] | 37 | 27
rqmF6GqjsiTpxVl0nmKs | 1 | Design Database for Customer | 0% | 05/06/2019 | 05/10/2019 | [10 empty] | 5 | 5
YvBSLmiogh6rLCNJUCwR | 1 | Create Database for Customer | 0% | 05/13/2019 | 05/28/2019 | [10 empty] | 16 | 12
88u7VmCOuaX26fT6PodW | 1 | Test Database for Customer | 0% | 05/29/2019 | 05/31/2019 | [10 empty] | 3 | 3
w58hTaJb0lxBBXy0ZIeo | 1 | Revise Database for Customer | 0% | 06/03/2019 | 06/11/2019 | [10 empty] | 9 | 7
1wQskmguR5Zd6jvqfN29 | 1 | Application Database: | 0% | [12 empty] | 37 | 27
STXZxXBPViHDeZ0tcNbx | 1 | Design Database for Application | 0% | 06/12/2019 | 06/18/2019 | [10 empty] | 7 | 5
noiZb8bHJJx8bIGSHNiR | 1 | Create Database for Application | 0% | 06/19/2019 | 07/04/2019 | [10 empty] | 16 | 12
2F0QBix8pbYLR47LarP7 | 1 | Test Database for Application | 0% | 07/05/2019 | 07/09/2019 | [10 empty] | 5 | 3
5pJqqeuzku8BFjorNdvr | 1 | Revise Database for Application | 0% | 07/10/2019 | 07/18/2019 | [10 empty] | 9 | 7
F4MDgxNL36FbKUSX9fYN | 1 | Bank Account Database: | 0% | [12 empty] | 39 | 27
i7gugu4BCKjtzzpebqeh | 1 | Design Database for Bank Account | 0% | 07/19/2019 | 07/25/2019 | [10 empty] | 7 | 5
H2g0ZnrQOmpve50kCKL5 | 1 | Create Database for Bank Account | 0% | 07/26/2019 | 08/12/2019 | [10 empty] | 18 | 12
xMxvuTvUX2OxMGxwJS8n | 1 | Test Database for Bank Account | 0% | 08/13/2019 | 08/15/2019 | [10 empty] | 3 | 3
nSKi2D3L4dGH6i81sarf | 1 | Revise Database for Bank Account | 0% | 08/16/2019 | 08/26/2019 | [10 empty] | 11 | 7
43lsqHfvRDyp5NmR7bdx | 1 | Payment Database: | 0% | [12 empty] | 37 | 27
3JQ5FES15zo79lRC72aa | 1 | Design Database for Payment | 0% | 08/27/2019 | 09/02/2019 | [10 empty] | 7 | 5
s2e1nsoRn1eoh5yI8lO8 | 1 | Create Database for Payment | 0% | 09/03/2019 | 09/18/2019 | [10 empty] | 16 | 12
0ZD5sG3wS9fLbVZeksDw | 1 | Test Database for Payment | 0% | 09/19/2019 | 09/23/2019 | [10 empty] | 5 | 3
ZsbZ0pLzloqlPm1dgprb | 1 | Revise Database for Payment | 0% | 09/24/2019 | 10/02/2019 | [10 empty] | 9 | 7
BVPd7Gj0RwrJbTBIKerE | 1 | Milestone 1 (Database) | 0% | 10/02/2019 | 10/02/2019 | [10 empty] | 1 | 1
CUDQ6TURml3Oig1HUDQt | 1 | Account Registration: | 0% | [12 empty] | 24 | 18
yNVd16kHyp8LfxrUca6Z | 1 | Design Account Registration Form | 0% | 06/12/2019 | 06/14/2019 | [10 empty] | 3 | 3
Km6rM12b6MuIr8vetQTP | 1 | Create Account Registration Form | 0% | 06/17/2019 | 06/24/2019 | [10 empty] | 8 | 6
yL3wGPizYf93GhHapt4S | 1 | Create Controller for Account Registration Form | 0% | 06/25/2019 | 06/27/2019 | [10 empty] | 3 | 3
9UqpSf9fx5X90kdxrJxj | 1 | Test Account Registration | 0% | 06/28/2019 | 07/02/2019 | [10 empty] | 5 | 3
R0y5bSt0QYGn08CHFBdR | 1 | Revise Account Registration | 0% | 07/03/2019 | 07/05/2019 | [10 empty] | 3 | 3
ZWCM3yyyEXWL4p2I50gG | 1 | Account Login: | 0% | [12 empty] | 24 | 18
ZxmsxH1uqeh4xP12kMoR | 1 | Create Controller for Account Login Form | 0% | 07/08/2019 | 07/10/2019 | [10 empty] | 3 | 3
ohnnDzCjI2P2mcOMzNlO | 1 | Design Account Login Form | 0% | 07/11/2019 | 07/18/2019 | [10 empty] | 8 | 6
YmqRfMx7unX7kIaiVbcA | 1 | Create Account Login Form | 0% | 07/19/2019 | 07/23/2019 | [10 empty] | 5 | 3
4NZg6IZHNkik6Ltrqldh | 1 | Test Account Login | 0% | 07/24/2019 | 07/26/2019 | [10 empty] | 3 | 3
2S4iEfpiKlcXwY5ZgG1v | 1 | Revise Account Login | 0% | 07/29/2019 | 07/31/2019 | [10 empty] | 3 | 3
bM6g2TWj3SuOlBWxootc | 1 | Milestone 2 (Customer Account Management) | 0% | 07/31/2019 | 07/31/2019 | [10 empty] | 1 | 1
nMJVmptR6ZnHHGTJFeyk | 1 | Link Application: | 0% | [12 empty] | 26 | 18
SRBtzEyjGFwDDEq4MylD | 1 | Design Link Application Form | 0% | 07/19/2019 | 07/23/2019 | [10 empty] | 5 | 3
KdxCoNA2YYevmdRitgr9 | 1 | Create Link Application Form | 0% | 07/24/2019 | 07/31/2019 | [10 empty] | 8 | 6
07qC6Tn32hjeVmZMVM8m | 1 | Create Controller for Link Application Form | 0% | 08/01/2019 | 08/05/2019 | [10 empty] | 5 | 3
XwJ3E7r8q7H4IddXqduR | 1 | Test Link Application | 0% | 08/06/2019 | 08/08/2019 | [10 empty] | 3 | 3
GaFOjc4ylraPlySjlM0p | 1 | Revise Link Application | 0% | 08/09/2019 | 08/13/2019 | [10 empty] | 5 | 3
07NoRC0bsGfeViulQ9Hx | 1 | View Balance: | 0% | [12 empty] | 16 | 12
KsvcxM3MhlqJsXn7eJd5 | 1 | Implement Viewing Balance | 0% | 08/27/2019 | 09/03/2019 | [10 empty] | 8 | 6
keczwWx3MbuJwzwbUyjl | 1 | Test Viewing Balance | 0% | 09/04/2019 | 09/06/2019 | [10 empty] | 3 | 3
OmQ5AAUjCQapjrtRBW2B | 1 | Revise Viewing Balance | 0% | 09/09/2019 | 09/11/2019 | [10 empty] | 3 | 3
mDdQBabHbTJp9Tv7qDLE | 1 | View Transaction History: | 0% | [12 empty] | 21 | 15
af7bva87rcbMPIgVpC2q | 1 | Design Transaction History Viewer | 0% | 09/12/2019 | 09/16/2019 | [10 empty] | 5 | 3
jhPbKYaTz01f69vExGsN | 1 | Create Transaction History Viewer | 0% | 09/17/2019 | 09/24/2019 | [10 empty] | 8 | 6
LSu40MEFUjXwH8DSPagB | 1 | Test Viewing Transaction History | 0% | 09/25/2019 | 09/27/2019 | [10 empty] | 3 | 3
NXSt4ptGNMhOGfu3IYtH | 1 | Revise Viewing Transaction History | 0% | 09/30/2019 | 10/02/2019 | [10 empty] | 3 | 3
SGBxz6pHOdi2CSilgwVh | 1 | Fund Transfer: | 0% | [12 empty] | 24 | 18
pdxEhcWH4hNZXgsK1TWL | 1 | Design Fund Transfer Form | 0% | 08/27/2019 | 08/29/2019 | [10 empty] | 3 | 3
SaY56FdgXJ9skqyA3Mre | 1 | Create Fund Transfer Form | 0% | 08/30/2019 | 09/06/2019 | [10 empty] | 8 | 6
3HEkVSmF7XKmtpujrnIF | 1 | Create Controller for Fund Transfer Form | 0% | 09/09/2019 | 09/11/2019 | [10 empty] | 3 | 3
s8V5WhqSuNGFA2M2fXrk | 1 | Test Fund Transfer | 0% | 09/12/2019 | 09/16/2019 | [10 empty] | 5 | 3
VgAZjlOTYKWDeyW9Rfuq | 1 | Revise Fund Transfer | 0% | 09/17/2019 | 09/19/2019 | [10 empty] | 3 | 3
8dvnsgl0dPjUQWQ6hyGU | 1 | Milestone 4 (Fund Transfer) | 0% | 09/19/2019 | 09/19/2019 | [10 empty] | 1 | 1
0CxNbp0l50vnxVcEUSSV | 1 | Bill Payment: | 0% | [12 empty] | 37 | 27
W4quxfPSmJvM7LmbcfNP | 1 | Design Scheduled Payment Viewer | 0% | 10/03/2019 | 10/07/2019 | [10 empty] | 5 | 3
xVBMqQwJsckejQVnjXPD | 1 | Create Scheduled Payment Viewer | 0% | 10/08/2019 | 10/15/2019 | [10 empty] | 8 | 6
j2ksfg8QMoShIWpTM2R2 | 1 | Design Bill Payment Form | 0% | 10/16/2019 | 10/18/2019 | [10 empty] | 3 | 3
J4P2oYLvQRmhPy7nEsXq | 1 | Create Bill Payment Form | 0% | 10/21/2019 | 10/28/2019 | [10 empty] | 8 | 6
63SqWBqHfz46gwrexKmQ | 1 | Create Controller for Bill Payment Form | 0% | 10/29/2019 | 10/31/2019 | [10 empty] | 3 | 3
ZMbISB2DTThM9ODcC3PR | 1 | Test Bill Payment | 0% | 11/01/2019 | 11/05/2019 | [10 empty] | 5 | 3
cyr7dSsBh6k3c5w8U10C | 1 | Revise Bill Payment | 0% | 11/06/2019 | 11/08/2019 | [10 empty] | 3 | 3
8D9FfZzPQN8yrMbAjfka | 1 | Milestone 5 (Bill Payments) | 0% | 11/08/2019 | 11/08/2019 | [10 empty] | 1 | 1
xvCdOSlCq9hbGk73LNq8 | 1 | Export Electronic Statement: | 0% | [12 empty] | 16 | 12
PHrhGh7BEWFCVNVutQQR | 1 | Implement Exporting Electronic Statement | 0% | 10/03/2019 | 10/10/2019 | [10 empty] | 8 | 6
FkvRP2P7xjK0NSI1qfXF | 1 | Test Exporting Electronic Statement | 0% | 10/11/2019 | 10/15/2019 | [10 empty] | 5 | 3
2nvLVQoKJk7Br9N6QncO | 1 | Revise Exporting Electronic Statement | 0% | 10/16/2019 | 10/18/2019 | [10 empty] | 3 | 3
q5bBJRABcvby1yTRpMCW | 1 | Milestone 3 (Bank Account Related Services) | 0% | 10/18/2019 | 10/18/2019 | [10 empty] | 1 | 1
wZFWuTZtAsJLWfm4LsJt | 1 | View Nearby ATM Locations: | 0% | [12 empty] | 16 | 12
k8kVUIpYrdcxqvAd9fej | 1 | Implement Viewing Nearby ATM Locations | 0% | 06/12/2019 | 06/19/2019 | [10 empty] | 8 | 6
6lVgmbKt33xsjKctmHOR | 1 | Test Viewing Nearby ATM Locations | 0% | 06/20/2019 | 06/24/2019 | [10 empty] | 5 | 3
koYrrCZUDirzEkdcritr | 1 | Revise Viewing Nearby ATM Locations | 0% | 06/25/2019 | 06/27/2019 | [10 empty] | 3 | 3
xIerurqi6dI1Gik02169 | 1 | Milestone 7 (Non-Bank Account Related Services) | 0% | 06/27/2019 | 06/27/2019 | [10 empty] | 1 | 1
3nkDZVfyRiUDLeLA7iEe | 1 | Manage Link Application: | 0% | [12 empty] | 37 | 27
8NhoMqXxXcBHwpR2owNo | 1 | Design Link Application Viewer | 0% | 08/14/2019 | 08/16/2019 | [10 empty] | 3 | 3
dYMI7YvTDpudqmPGeaEO | 1 | Create Link Application Viewer | 0% | 08/19/2019 | 08/26/2019 | [10 empty] | 8 | 6
CUjk8oI1bkAQAu91jcru | 1 | Design Managing Link Application Menu | 0% | 08/27/2019 | 08/29/2019 | [10 empty] | 3 | 3
NUr2EKrmWE4QlMa950Cm | 1 | Create Managing Link Application Menu | 0% | 08/30/2019 | 09/06/2019 | [10 empty] | 8 | 6
0OWh6uUUPNO7dd4ExLPs | 1 | Create Controller for Managing Link Application Menu | 0% | 09/09/2019 | 09/11/2019 | [10 empty] | 3 | 3
ifhrI7VXY5KEZ0ta3eur | 1 | Test Managing Link Application | 0% | 09/12/2019 | 09/16/2019 | [10 empty] | 5 | 3
nuGuwb28LAOijJgNQ74s | 1 | Revise Managing Link Application | 0% | 09/17/2019 | 09/19/2019 | [10 empty] | 3 | 3
fxksZtkgoTWH3TNqwKT1 | 1 | Milestone 2 (Bank Account Links) | 0% | 09/19/2019 | 09/19/2019 | [10 empty] | 1 | 1
n8jpXxyhNbfCoGgOYSM7 | 1 | Component Integration: | 0% | [12 empty] | 40 | 30
4yEAiA3YYFST3PSMlpgt | 1 | Integrate Built Components into One Whole System | 0% | 11/11/2019 | 12/04/2019 | [10 empty] | 24 | 18
s5E0eH11N2bXDoqVDnjO | 1 | Test System as a Whole | 0% | 12/05/2019 | 12/12/2019 | [10 empty] | 8 | 6
mhQEqp2T8k6bY6BVzU1w | 1 | Revise as Needed | 0% | 12/13/2019 | 12/20/2019 | [10 empty] | 8 | 6
1IX6NpoOIKFUyOneKwmC | 1 | Milestone 8 (Component Integration) | 0% | 12/20/2019 | 12/20/2019 | [10 empty] | 1 | 1